## Sheet1
CS401 Group 1 Meeting Minutes
Date: | Attendance | Started | Ended | What was Done | What was Confirmed
September 29 2023 | David, Madison, Sean | 3:15PM | 5:40PM | Worked on Class Diagram and Use case Diagram
October 1 2023 | David, Madison, Sean | 3:10PM | 5:40PM | Worked on Class Diagram, Sequence Diagram, and SRS Doc
October 2 2023 | Sedat, David, Madison, Sean | 5:47PM | 7:22PM | Worked on SRS Doc, Class Diagram, Gantt Chart, and slides for the presentation
October 4 2023 | Sedat, David, Madison, Sean, Joseph | 5:37PM | 7:37PM | Worked on Presentation slides - Adding Class and Sequence
October 14 2023 | David, Madison, Sean | 6:00PM | 7:05PM | Redid use case diagram | User sends a message -> sent to the server -> writes to room file
October 15 2023 | Sedat, Madison, Joseph, David, Sean | 7:00PM | 8:00PM | Finish up Presentation Slides
October 21 2023 | Sedat, Madison, Joseph, David, Sean | 7:10PM | 8:35PM | Figuring out what are we supposed to do next in the project
October 28 2023 | Sedat, Madison, Sean | 7:00PM | 9:30PM | Worked on Presentation slides and class diagram - Adding Structure of Presentation | Chatrooms UID are based off of the users in the room (it is created when the first message is sent), User ID are based on the first letter of the first name and the first letter of their last name followed by 5 digits
October 29 2023 | Joseph, Madison, Sean | 7:00PM | 8:00PM | Finish up Presentation Slides for Design
November 2 2023 |  | 7:00PM
November 16 2023 | Sedat, David, Madison, Sean, Joseph | 1:15PM |  | Worked on the java files of application