## Gantt Chart Template
https://goo.gl/PXLbMe
| PROJECT TITLE | CLack |  |  |  |  | COMPANY NAME | [8 empty] | Group 1
[7 empty] | DATE | [8 empty] | 2023-10-02
[22 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE/PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Requirements
1.1 | Meet people in group | Everyone | 2023-08-22 | 2023-08-22 | 1 | 100% | bar: WEEK 1 T
1.1.1 | Come up with 10 requirement | Everyone | 2023-08-31 | 2023-09-07 | 7 | 100% | bar: WEEK 2 R to WEEK 3 R
1.2 | First Presentation | Everyone | 2023-09-07 | 2023-09-07 | 1 | 100% | bar: WEEK 3 R
1.3 | Come up with 5 Class Candidates | Sean | 2023-09-30 |  | 5 | 100%
1.4 | Finshing All Docs | Everyone | 2023-09-30 | 2023-10-04 | 4 | 100% | bar: WEEK 6 F to WEEK 7 W
1.5 | Second Presentation | Everyone | 2023-10-05 | 2023-10-05 | 1 | 100% | bar: WEEK 7 M to WEEK 7 W
1.6 | Add everything to github repo | Madison | 2023-10-05 | 2023-10-05 | 1 | 100% | bar: WEEK 7 W
2 | Design
2.1 | [5 empty] | 0%
2.2 | [5 empty] | 0%
2.3 | [5 empty] | 0%
2.4 | [5 empty] | 0%
2.5 | [5 empty] | 0%
3 | Implementaion
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.2.1 | [5 empty] | 0%
3.2.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.3.1 | [5 empty] | 0%
4 | Testing
4.1 | [5 empty] | 0%
4.2 | [5 empty] | 0%
4.3 | [5 empty] | 0%
4.4 | [5 empty] | 0%