## Gantt Chart Template
https://goo.gl/PXLbMe
| PROJECT TITLE | CLack |  |  |  |  | COMPANY NAME | [8 empty] | Group 1
[7 empty] | DATE | [8 empty] | 2023-10-02
[22 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE/PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Requirements
1.1 | Meet people in group | Everyone | 2023-08-22 | 2023-08-22 | 1 | 100% | bar: WEEK 1 T; WEEK 10 W to WEEK 10 F
1.1.1 | Come up with 10 requirement | Everyone | 2023-08-31 | 2023-09-07 | 7 | 100% | bar: WEEK 2 R to WEEK 3 R; WEEK 10 W to WEEK 10 F
1.2 | First Presentation | Everyone | 2023-09-07 | 2023-09-07 | 1 | 100% | bar: WEEK 3 R; WEEK 10 W to WEEK 10 F
1.3 | Come up with 5 Class Candidates | Sean | 2023-09-30 |  | 5 | 100% | bar: WEEK 10 W to WEEK 10 F
1.4 | Finshing All Docs | Everyone | 2023-09-30 | 2023-10-04 | 4 | 100% | bar: WEEK 6 F to WEEK 7 W; WEEK 10 W to WEEK 10 F
1.5 | Second Presentation | Everyone | 2023-10-05 | 2023-10-05 | 1 | 100% | bar: WEEK 7 M to WEEK 7 W; WEEK 10 W to WEEK 10 F
1.6 | Add everything to github repo | Madison | 2023-10-05 | 2023-10-05 | 1 | 100% | bar: WEEK 7 W; WEEK 10 W to WEEK 10 F
2 | Design
2.1 | Design Presentation | Everyone | 2023-10-21 | 2023-10-31 | 7 | 100% | bar: WEEK 10 M to WEEK 11 T
2.2 | GUI Design | Sean | 2023-10-21 | 2023-10-25 | 3 | 100% | bar: WEEK 10 M to WEEK 11 T
2.3 | GUI Class | Sean | 2023-10-25 | 2023-10-28 | 3 | 100%
2.4 | Server / Server Handler | Madison | 2023-10-21 | 2023-10-27 | 3 | 100% | bar: WEEK 10 W to WEEK 10 F
2.5 | Chatroom / ChatHistory / Logging | Sedat | 2023-10-21 | 2023-10-30 | 3 | 100% | bar: WEEK 10 W to WEEK 10 F
2.6 | Client | Joseph | 2023-10-21 | 2023-10-30 | 3 | 100% | bar: WEEK 10 W to WEEK 10 F
2.7 | User / IT | David | 2023-10-21 | 2023-10-30 | 3 | 100% | bar: WEEK 10 W to WEEK 10 F
3 | Implementaion
3.1 | GUI Class | Sean | 2023-11-03 | 2023-11-17 | 11 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 11 F to WEEK 13 F
3.2 | Server / Server Handler | Madison | 2023-11-03 | 2023-11-17 | 11 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 11 F to WEEK 13 F
3.3 | Client | Joseph | 2023-11-03 | 2023-11-17 | 11 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 11 F to WEEK 13 F
3.4 | Chatroom / ChatHistory | Sedat | 2023-11-03 | 2023-11-17 | 11 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 11 F to WEEK 13 F
3.5 | User / IT/ Authentication | David | 2023-11-03 | 2023-11-17 | 11 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 11 F to WEEK 13 F
3.6 | Messages over the network | Joseph, Madison | 2023-11-17 | 2023-11-24 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 13 F to WEEK 14 F
3.7 | Logging | Sedat, David | 2023-11-17 | 2023-11-24 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 13 F to WEEK 14 F
3.8 | Get them all to work together (senf the first message over network) | Everyone | 2023-11-17 | 2023-11-24 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 13 F to WEEK 14 F
4 | Testing (JUnit)
4.1 | GUI Class | Sean | 2023-11-27 | 2023-12-01 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 15 M to WEEK 15 F
4.2 | Server / Server Handler | Madison | 2023-11-27 | 2023-12-01 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 15 M to WEEK 15 F
4.3 | Client | Joseph | 2023-11-27 | 2023-12-01 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 15 M to WEEK 15 F
4.4 | Chatroom / ChatHistory | Sedat | 2023-11-27 | 2023-12-01 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 15 M to WEEK 15 F
4.5 | User / IT/ Authentication | David | 2023-11-27 | 2023-12-01 | 6 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 15 M to WEEK 15 F
4.6 | Final Presentation | Everyone | 2023-11-17 | 2023-12-07 | 15 | 0% | bar: WEEK 10 W to WEEK 10 F; WEEK 15 M to WEEK 15 F; WEEK 16 R