## Sheet1
CS401 Group 1 Meeting Minutes
Date: | Attendance | Started | Ended | What was Done | What was Confirmed
September 29 2023 | David, Madison, Sean | 3:15PM | 5:40PM | Worked on Class Diagram and Use case Diagram
October 1 2023 | David, Madison, Sean | 3:10PM | 5:40PM | Worked on Class Diagram, Sequence Diagram, and SRS Doc
October 2 2023 | Sedat, David, Madison, Sean | 5:47PM | 7:22PM | Worked on SRS Doc, Class Diagram, Gantt Chart, and slides for the presentation
October 4 2023 | Sedat, David, Madison, Sean, Joseph | 5:37PM | 7:37PM | Worked on Presentation slides - Adding Class and Sequence
October 14 2023 | David, Madison, Sean | 6:00PM | 7:05PM | Redid use case diagram | User sends a message -> sent to the server -> writes to room file
October 15 2023 | Sedat, Madison, Joseph, David, Sean | 7:00PM | 8:00PM | Finish up Presentation Slides
October 21 2023 | Sedat, Madison, Joseph, David, Sean | 7:10PM | 8:35PM | Figuring out what are we supposed to do next in the project
October 28 2023 | Sedat, Madison, Sean | 7:00PM